## Planning Phase
Risk |  | Initial Risk |  |  | Proposed Control Measures |  | Revised Risk |  |  | Selected | Actions |  | Initial Scores |  |  | Initial Scores
Source | Event | Likelihood | Consequence | Rating | Options | Considerations | Likelihood | Consequence | Rating |  | Who | What | L | C |  | L | C
Vulnerable Road Users - pedestrians, cyclists, people with disabilities and wheeled path users | [14 empty] | Very High
Works impact on existing path routes resulting in VRU unable to pass the site safely using existing paths | VRUs cross roads in an unsafe manner at unsigned locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
| VRUs use a temporary path route which has a surface not appropriate for wheeled path users, visually impaired and VRU with mobility issues. Results in trip or fall hazards |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Medium | 0 | 0
| VRUs diverted to a detour route which is an unacceptable length with a lower likelihood of VRUs using the defined route |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Low | 0 | 0
| VRUs following unfamiliar and illegible paths due to lack of clear direction interact with work site vehicles, equipment or other vehicles moving through the site. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Negligible | 0 | 0
| VRUs confused by TTM layout and follow incorrect route into site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Select L & C | 0 | 0
| VRUs entering live traffic lanes in unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| VRUs confused by TTM layout or path direction is not clear - and follow unsafe route around site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Works impact on existing crossings resulting in VRU unable to use the existing crossing route | Altered crossing is not clear to path users leading to unpredictable pedestrian behaviour when crossing roads |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Safe school crossing practices compromised resulting in children crossing the road in an an unsafe and unpredictable manner in and around the site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Schools, clubs or other facilities that may generate high volumes of pedestrian or cycle traffic | Temporary or impacted path route has inadequate capacity leading to VRUs crossing at unsafe locations or travelling along the road leading to conflicts between path users and traffic, or to conflicts between VRUs and worksite hazards, plant movements or unsuitable routes |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Facilities such as hotels or taverns where pedestrians may have their judgement impaired | VRUs may be confused by temporary alternative routes and enter the worksite of live traffic lanes at unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C
High cycle volumes on road or in defined bicycle lane / shoulder which is impacted by works | Cyclist transition to footpath does not occur at a safe location leading to possible cyclist injury or conflict with other path users |  |  | Select L & C |  |  |  |  | Select L & C
| Cyclist merge with general traffic lanes at unsafe location or in unsafe manner leading to collision with other road vehicles. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Traffic Impacts | [12 empty] | 0 | 0 |  | 0 | 0
Excessive length of worksite, including rural areas | Dangerous / agressive driver behaviour resulting from excessive length of queues because of time needed to manage reversible flow leading to lack of community / road user acceptance of the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Infrequently used property access in the middle of the site may not be adequately monitored resulting in unsafe site entry |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Long queues combined with inadequate warning of traffic queue results in collision at end of queue |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Detouring of traffic from a major or multi-lane road | Volume of detoured traffic has unacceptable impact on surrounding areas including - property and business access is compromised - Increased volume of traffic on residential streets leading to compromised safety outcomes for residents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Detoured traffic experiences unacceptable delays |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Detouring of traffic onto roads with height, length or weight restrictions | Some detoured vehicles cannot negotiate the defined detour creating - delays and congestion while reversing or turning - damage to infrastructure - collisions with other vehicles |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Works lead to excessive and unacceptable traffic queues and delays. Can be due to - not maintaining min available req. lanes - closure of high volume roads | Aggressive driver behaviour and lack of community acceptance of worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Traffic volumes not suitably accommodaed leading to congestion / delays exceeds allowable levels |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Extended queue lengths, or road alignment factors affect sight distance to the end of queue, leads to netowrk crash risks |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Volume of traffic in remaining lanes is unacceptably high leading to traffic queues extend through nearby intersections / roundabouts |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Interference with the operation of permanent traffic signals | Compromised legibility of traffic controls for road users leads to road user confusion leading to increased likelihood of traffic incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Increased congestion due to works results in queued traffic through signalised intersections leading to unsafe operation of the intersection |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Closure of turning movements and banning of movements at intersections | Closure of turning movements with no clear alternative leads to road user confusion and increased likelihood of traffic incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Volume of detoured traffic has unacceptable impact on surrounding areas including - property and business access is compromised - Increased congestion on other parts of the road network leading to compromised safety outcomes |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Speed choices | [12 empty] | 0 | 0 |  | 0 | 0
Reductions in speed limits, considering the safety of workers and road users are not considered credible to drivers | Road users travel at inappropriate speeds due to lack of understanding of applicable speed limits leads to increased likelihood and severity of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Special work speed limits less than 40km/h required for specific hazards | Road users travel at inappropriate speeds due to lack of understanding of applicable speed limits leads to increased likelihood and severity of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Worksite operations | [12 empty] | 0 | 0 |  | 0 | 0
Site in operation during times of night / low visibility | Sight distance or vision of road user compromised on approach to worksite results in road user unable to respond in a timely manner to the hazard ahead |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Periods in which work can and cannot occur | Work occurs at inappropriate times of the day - Disruption of residential areas - Interference with known peak traffic times - Frequent interference with usual business activity - Dust and noise impacts on surrounding areas |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TMP implemention for excessive time within a single shift | Staff fatigue leads to decreased concentration of road workers leading to increased likelihood of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Emergency Vehicles | [12 empty] | 0 | 0 |  | 0 | 0
Works lead to excessive traffic queues and delays leads to unacceptably long delays to road users | Emergency vehicles access past the works area is blocked by works activities or queued traffic leading to unacceptable delays to emergency vehicles |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Emergency vehicle access to the worksite not clear | Extended delay to attend to injured workers or road users at the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Public Transport |  |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Public transport stops and routes located in works area - impact on provision of usual services | Negative community perception of the impact of the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Unpredictable public transport vehicle movements and passenger movements near the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Site Access | [12 empty] | 0 | 0 |  | 0 | 0
Site access for construction vehicles is not clearly defined / managed | Construction vehicles stop / queue in unsafe locations causes conflicts with VRUs or congestion for passing traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Construction vehicles use inapporpriate entry and exit points leading to colisions with traffic.
| Passing traffic inadvertently enters worksites leading to worker injury due to unexpected vehicle entry to worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Property Access | [12 empty] | 0 | 0 |  | 0 | 0
Closure or roads or turn movements at intersections affects adjoining properties with access near or at the site | Vehicle access to properties compromised by road closures or delays leads to decreasd community acceptance of the presence of the worksite. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Rural property access and stock crossings within the worksite | disruption of essential stock crossing movemenets and disruption of local rural economic activity |  |  | Select L & C |  |  |  |  | Select L & C
Parking facilities exist within the proposed worksite | Reduction in available parking facilities leads to illegal or unsafe parking practices in and around the worksite. |  |  | Select L & C |  |  |  |  | Select L & C
Environmential and site features | [12 empty] | 0 | 0 |  | 0 | 0
Features at the site reduce sight distance or vision of TTM devices | Road users unable to adequately comprehend messages and react in time leading to potential injury to road users and workers or damage at the works site. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Vegetation obscures positioning of signs and devices | Road users is unaware of the approaching worksite and potential queues leading ot collision. |  |  | Select L & C |  |  |  |  | Select L & C
Existing signage, pavement markings and other features conflict with the proposed TTM treatments | Compomised legibility of worksite leads ot driver confusion |  |  | Select L & C |  |  |  |  | Select L & C
Works taking place during seasons with increased pssibility of electrical storms | Lightning risk to TC and other staff causes delays to works schedule or completion of works within defined daily time restrictions |  |  | Select L & C |  |  |  |  | Select L & C
Shadowing, fog, glare, inclement weather, smoke | Reduced visibility for approaching traffic - increased risk to road users and road workers |  |  | Select L & C |  |  |  |  | Select L & C
Night works | Reduced legibilty of worksite |  |  | Select L & C |  |  |  |  | Select L & C
| Visual overload with retroflective devices |  |  | Select L & C |  |  |  |  | Select L & C
Site constraints with no escape route for workers or traffic controllers | Workers cannot escape traffic incidents on site and are injured by vehicle intrusion into the site. |  |  | Select L & C |  |  |  |  | Select L & C
Low quality road surfacing | Damage to vehicles and worksite equipment |  |  | Select L & C |  |  |  |  | Select L & C
Multilane roads with inadequate median width to not allow duplication of devices in the median | Drivers in right lane(s) do not have visibility of TTM devices placed on the left verge and are unaware of the approproaching worksite or the apporpriate actions they are required to take leading to potential late unsafe merging movements or entry to the worksite. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Specifications / standards / practices | [12 empty] | 0 | 0 |  | 0 | 0
Clarity of applicable specifications, standards, rules and policies including conflict between requirements from RIM / PCBU etc. Documentation of superceded standards. | Application of incorrect or expired specifications, standards, rules and policies leads to confusion regarding mandatory safety regulations leading to inconsistent application and worksite not in line with required safety standards |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Stakeholders | [12 empty] | 0 | 0 |  | 0 | 0
Stakeholders inadequately consulted regarding the project and its impacts leading to opposition to project | Delays as complaints are addressed and resolved |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Heavy / Oversize vehilcles | [12 empty] | 0 | 0 |  | 0 | 0
Accommodation of truck traffic and over-sized loads | inadequate lane widths, provision for turning movements or vertical alignments leads to vehicles unable to negotiate defined traffic route and collide with other vehicles or worksite devices / plant |  |  | Select L & C |  |  |  |  | Select L & C
Like - lihood
Conse - quence
Rating
Measures selected will generally only reduce the likelihood or consequence of an event, usually not both. Ensure adequate justification is documented here or elsewhere to support the proposed revised ratings.

## Design Phase
Risk |  | Initial Risk |  |  | Proposed Control Measures |  | Revised Risk |  |  | Selected | Actions |  | Initial Scores |  |  | Initial Scores
Source | Event | Likelihood | Consequence | Rating | Options | Considerations | Likelihood | Consequence | Rating |  | Who | What | L | C |  | L | C
Vulnerable Road Users - pedestrians, cyclists, people with disabilities and wheeled path users | [14 empty] | Very High
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Works impact on existing path routes resulting in VRU unable to pass the site safely using existing paths | VRUs cross roads in an unsafe manner at unsigned locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
| VRUs use a temporary path route which has a surface not appropriate for wheeled path users, visually impaired and VRU with mobility issues. Results in trip or fall hazards |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Medium | 0 | 0
| VRUs diverted to a detour route which is an unacceptable length with a lower likelihood of VRUs using the defined route |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Low | 0 | 0
| VRUs following unfamiliar and illegible paths due to lack of clear direction interact with work site vehicles, equipment or other vehicles moving through the site. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Negligible | 0 | 0
| VRUs confused by TTM layout and follow incorrect route into site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Select L & C | 0 | 0
| VRUs entering live traffic lanes in unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| VRUs confused by TTM layout or path direction is not clear - and follow unsafe route around site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Works impact on existing crossings resulting in VRU unable to use the existing crossing route | Altered crossing is not clear to path users leading to unpredictable pedestrian behaviour when crossing roads |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Safe school crossing practices compromised resulting in children crossing the road in an an unsafe and unpredictable manner in and around the site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Schools, clubs or other facilities that may generate high volumes of pedestrian or cycle traffic | Temporary or impacted path route has inadequate capacity leading to VRUs crossing at unsafe locations or travelling along the road leading to conflicts between path users and traffic, or to conflicts between VRUs and worksite hazards, plant movements or unsuitable routes |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Facilities such as hotels or taverns where pedestrians may have their judgement impaired | VRUs may be confused by temporary alternative routes and enter the worksite of live traffic lanes at unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
High cycle volumes on road or in defined bicycle lane / shoulder which is impacted by works | Cyclist transition to footpath does not occur at a safe location leading to possible cyclist injury or conflict with other path users |  |  | Select L & C |  |  |  |  | Select L & C
| Cyclist merge with general traffic lanes at unsafe location or in unsafe manner leading to collision with other road vehicles. |  |  | Select L & C |  |  |  |  | Select L & C
Additional design phase items
Works impact on existing path routes - pedestrians diverted to alternative existing path routes | Alternative path route is a lesser quality / standard than impacted route creating slip / trip / fall hazards for path users or hazards when path users need to pass each other - path width - path surface - path grade - lighting |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Works impact on existing path routes - pedestrians diverted to temporary path routes | Temporary path route is a lesser quality / standard than impacted route creating slip / trip / fall hazards for path users or hazards when path users need to pass each other - path width - path surface - path grade - lighting |  |  | Select L & C |  |  |  |  | Select L & C
Works impact on existing path routes - pedestrians diverted to temporary route on the road surface | Collision between diverted path users and traffic due to - inadequate separation between traffic and pedestrians - inadequate reduction in vehicle speeds past the worksite - inadequate protection / barriers to separate path from road |  |  | Select L & C
Works impact on existing path routes - pedestrians diverted across roads at new or existing crossing points | Alternative / Temporary crossing of roads creating conflict with traffic due to - inadequate controls for pedestrians in periods of high traffic - inadeqate sight distance at crossing points - indequate ramps / transition from path to road |  |  | Select L & C |  |  |  |  | Select L & C
Temporary path route ot TTM devices restrict sight distances between pathways and intersections, driveways and site access points | VRUs and/or drivers unable to see potential conflict situations leading to collisions |  |  | Select L & C |  |  |  |  | Select L & C
TTM devices and signage are located in road shoulders, bicycle lanes, or immediately adjaent to paths | Risk to cyclists using the road corridor - colliding with TTM devices - being diverted unsafely into traffic lanes - being diverted to alternative facilities at unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C
Traffic Impacts | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Excessive length of worksite, including rural areas | Dangerous / agressive driver behaviour resulting from excessive length of queues because of time needed to manage reversible flow leading to lack of community / road user acceptance of the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Infrequently used property access in the middle of the site may not be adequately monitored resulting in unsafe site entry |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Long queues combined with inadequate warning of traffic queue results in collision at end of queue |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Detouring of traffic from a major or multi-lane road | Volume of detoured traffic has unacceptable impact on surrounding areas including - property and business access is compromised - Increased volume of traffic on residential streets leading to compromised safety outcomes for residents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Detoured traffic experiences unacceptable delays |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Works lead to excessive and unacceptable traffic queues and delays. Can be due to - not maintaining min available req. lanes - closure of high volume roads | Aggressive driver behaviour and lack of community acceptance of worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Traffic volumes not suitably accommodaed leading to congestion / delays exceeds allowable levels |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Extended queue lengths, or road alignment factors affect sight distance to the end of queue, leads to netowrk crash risks |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Volume of traffic in remaining lanes is unacceptably high leading to traffic queues extend through nearby intersections / roundabouts |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Interference with the operation of permanent traffic signals | Compromised legibility of traffic controls for road users leads to road user confusion leading to increased likelihood of traffic incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Increased congestion due to works results in queued traffic through signalised intersections leading to unsafe operation of the intersection |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Closure of turning movements and banning of movements at intersections | Closure of turning movements with no clear alternative leads to road user confusion and increased likelihood of traffic incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Volume of detoured traffic has unacceptable impact on surrounding areas including - property and business access is compromised - Increased congestion on other parts of the road network leading to compromised safety outcomes |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Additional design phase items
Unexpected changes in traffic volumes | Increased congestion / delays leads to dangerous / agrssive driver behaviour and increased potential for wide network impacts and collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Speed choices | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Reductions in speed limits, considering the safety of workers and road users are not considered credible to drivers | Road users travel at inappropriate speeds due to lack of understanding of applicable speed limits leads to increased likelihood and severity of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Additional design phase items
Site features including road surface, road geometry, lane widths and proximity of plant and TTM devices to traffic are a hazard to traffic at permanent posted speed | Speed of traffic through the site is not safe for all road users during the works |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Worksite operations | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Site in operation during times of night / low visibility | Sight distance or vision of road user compromised on approach to worksite results in road user unable to respond in a timely manner to the hazard ahead |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Periods in which work can and cannot occur | Work occurs at inappropriate times of the day - Disruption of residential areas - Interference with known peak traffic times - Frequent interference with usual business activity - Dust and noise impacts on surrounding areas |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TMP implemention for excessive time within a single shift | Staff fatigue leads to decreased concentration of road workers leading to increased likelihood of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Additional design phase items
Incident in / near the work area involving a road accident, breakdown or crash into the worksite | Impacts on works activities, ability to complete works on time, and wider network imacts and delays. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Complex works require extended experience from field staff to ensure correct implementation | TTM devices are not installed in the correct location, order or to ensure effectiveness for the intended users leading to reduced comprehension by road users. |  |  | Select L & C |  |  |  |  | Select L & C
Complex works activities with multiple different TTM stages / TGS diagrams | TGS and site works not aligned with works not adequately protected |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Emergency Vehicles | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Works lead to excessive traffic queues and delays leads to unacceptably long delays to road users | Emergency vehicles access past the works area is blocked by works activities or queued traffic leading to unacceptable delays to emergency vehicles |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Emergency vehicle access to the worksite not clear | Extended delay to attend to injured workers or road users at the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Public Transport | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Public transport stops and routes located in works area - impact on provision of usual services | Negative community perception of the impact of the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Unpredictable public transport vehicle movements and passenger movements near the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Site Access | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Site access for construction vehicles is not clearly defined / managed | Construction vehicles stop / queue in unsafe locations causes conflicts with VRUs or congestion for passing traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Construction vehicles use inappropriate entry and exit points leading to colisions with traffic.
| Passing traffic inadvertently enters worksites leading to worker injury due to unexpected vehicle entry to worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Additional design phase items
Congestion at entry leads | Impacts on traffic flow creating wider network impacts and potential for collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Unscheduled deliveries | Impacts on traffic flow creating wider network impacts and potential for collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Exit from work site to high speed roads | Insufficient acceleration length leads to unsafe exit to the traffic stream and collisions with through traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Property Access | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Closure or roads or turn movements at intersections affects adjoining properties with access near or at the site | Vehicle access to properties compromised by road closures or delays leads to decreasd community acceptance of the presence of the worksite. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Rural property access and stock crossings within the worksite | disruption of essential stock crossing movemenets and disruption of local rural economic activity |  |  | Select L & C |  |  |  |  | Select L & C
Parking facilities exist within the proposed worksite | Reduction in available parking facilities leads to illegal or unsafe parking practices in and around the worksite. |  |  | Select L & C |  |  |  |  | Select L & C
Additional design phase items
TTM devices block sight lines for vehicles entering / exiting properties | Potential collisiopns between enetering / exiting traffic and through traffic on the road. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Parking facilities exist within the proposed worksite | Parked vehicles obstruct TTM devices or create hazardous situtations within the worksite. |  |  | Select L & C |  |  |  |  | Select L & C
Site & environmental features | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Features at the site reduce sight distance or vision of TTM devices | Road users unable to adequately comprehend messages and react in time leading to potential injury to road users and workers or damage at the works site. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Vegetation obscures positioning of signs and devices | Road users is unaware of the approaching worksite and potential queues leading ot collision.
Existing signage, pavement markings and other features conflict with the proposed TTM treatments | Compomised legibility of worksite leads ot driver confusion |  |  | Select L & C
Works taking place during seasons with increased pssibility of electrical storms | Lightning risk to TC and other staff causes delays to works schedule or completion of works within defined daily time restrictions |  |  | Select L & C
Shadowing, fog, glare, inclement weather, smoke | Reduced visibility for approaching traffic - increased risk to road users and road workers |  |  | Select L & C
Night works | Reduced legibilty of worksite |  |  | Select L & C
| Visual overload with retroflective devices |  |  | Select L & C
Site constraints with no escape route for workers or traffic controllers | Workers cannot escape traffic incidents on site and are injured by vehicle intrusion into the site. |  |  | Select L & C
Low quality road surfacing | Damage to vehicles and worksite equipment |  |  | Select L & C
Multilane roads with inadequate median width to not allow duplication of devices in the median | Drivers in right lane(s) do not have visibility of TTM devices placed on the left verge and are unaware of the approproaching worksite or the apporpriate actions they are required to take leading to potential late unsafe merging movements or entry to the worksite. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Additional design phase items
Excavations, stockpiles, barriers, plant lay-up and work locations | Hazard to drivers who inadvertantly enter the worksite, particularly at changes in road alignment (curves, merges, lateral shifts) |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Obstructions reducing sight distance along road alignment including barriers, stockpiles, gawk screens, and plant items | Inadequate sight distance for road users who are unable to avoid colliding with obstructions on the road or other vehicles who have stopped / slowed |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Works activities or changes in alignment of traffic lanes impacts on existing road lighting of the alignment | Reduced lighting of temporary alignments, or removal of permanent lighting increases potential collisions between traffic and obstacles on the road and other road users such as VRUs. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Works activities or changes in alignment of traffic lanes impacts on existing drainage of the alignment | Increased water flow across the road surface or ponding of water on the road surface reduces road traction leading to loss of control by road users. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Specifications / standards / practices | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Clarity of applicable specifications, standards, rules and policies including conflict between requirements from RIM / PCBU etc. Documentation of superceded standards. | Application of incorrect or expired specifications, standards, rules and policies leads to confusion regarding mandatory safety regulations leading to inconsistent application and worksite not in line with required safety standards |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Stakeholders | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Stakeholders inadequately consulted regarding the project and its impacts leading to opposition to project | Delays as complaints are addressed and resolved |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Heavy / Oversize vehilcles | [12 empty] | 0 | 0 |  | 0 | 0
Planning Phase items - need to be considered/reviewed in design phase as well unless closed out or deemed not applicable in planning phase
Accommodation of truck traffic and over-sized loads | inadequate lane widths, provision for turning movements or vertical alignments leads to vehicles unable to negotiate defined traffic route and collide with other vehicles or worksite devices / plant |  |  | Select L & C
Temporary Traffic Management Devices | [12 empty] | 0 | 0 |  | 0 | 0
Complex traffic arrangements requiring unusual sign arrangements, detailed VMS messages or multiple signs for a single hazard | Road users misunderstand the intention of traffic control devices causing confusion. |  |  | Select L & C
| Insufficient information conveyed to road users of the complex traffic arrangements leading to confusion |  |  | Select L & C
Road features makes it difficult for signs to be placed correctly | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TTM devices dislodged or removed due to wind, passing traffic, theft, vandalism | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Road alignment results in complex requirements for the alignment of TTM devies to ensure their visibility and comprehension by the intended road users | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Like - lihood
Conse - quence
Rating
Measures selected will generally only reduce the likelihood or consequence of an event, usually not both. Ensure adequate justification is documented here or elsewhere to support the proposed revised ratings.

## Implementation Phase
Risk |  | Initial Risk |  |  | Proposed Control Measures |  | Revised Risk |  |  | Selected | Actions |  | Initial Scores |  |  | Initial Scores
Source | Event | Likelihood | Consequence | Rating | Options | Considerations | Likelihood | Consequence | Rating |  | Who | What | L | C |  | L | C
Vulnerable Road Users - pedestrians, cyclists, people with disabilities and wheeled path users | [14 empty] | Very High
Unidentified path or unformed pedestrian route impacted by the works | VRUs cross roads in an unsafe manner at unsigned locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
| VRUs use a temporary path route which is not planned / designed. Results in trip or fall hazards or following unsafe route. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Medium | 0 | 0
| VRUs following unfamiliar and illegible paths due to lack of clear direction interact with work site vehicles, equipment or other vehicles moving through the site. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Low | 0 | 0
| VRUs confused by TTM layout and follow incorrect route into site |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Negligible | 0 | 0
| VRUs entering live traffic lanes in unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | Select L & C | 0 | 0
Works impact on existing crossings resulting in VRU unable to use the existing crossing route | Near miss incidents or dangerous crossing movements creating unsafe conflicts with traffic. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Pedestrians may have their judgement impaired by alcholol / drugs | VRUs may be confused by temporary alternative routes and enter the worksite of live traffic lanes at unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
High cycle volumes on road or in defined bicycle lane / shoulder which is impacted by works | Cyclist transition to footpath or road in a dangerous manner |  |  | Select L & C |  |  |  |  | Select L & C
Works activities impact on existing or temporary path routes | Path route is damaged creating slip / trip / fall hazards for path users or hazards when path users need to pass each other |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Works impact on existing path routes - pedestrians diverted to temporary route on the road surface | Collision between diverted path users and traffic |  |  | Select L & C
TTM devices restrict sight distances between pathways and intersections, driveways and site access points | VRUs and/or drivers unable to see potential conflict situations leading to collisions |  |  | Select L & C |  |  |  |  | Select L & C
TTM devices and signage are located in road shoulders, bicycle lanes, or immediately adjaent to paths | Risk to cyclists using the road corridor - colliding with TTM devices - being diverted unsafely into traffic lanes - being diverted to alternative facilities at unsafe locations |  |  | Select L & C |  |  |  |  | Select L & C
Traffic Impacts | [12 empty] | 0 | 0 |  | 0 | 0
Works lead to excessive and unacceptable traffic queues and delays. | Aggressive driver behaviour and lack of community acceptance of worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Traffic volumes not suitably accommodaed leading to congestion / delays exceeds allowable levels |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Traffic queues extend through nearby intersections / roundabouts |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Interference with the operation of permanent traffic signals | Queued traffic through signalised intersections leading to unsafe operation of the intersection |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Closure of turning movements and banning of movements at intersections | Road user confusion, illegal traffic movements and traffic driving through the worksite. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Unexpected changes in traffic volumes | Increased congestion / delays leads to dangerous / agrssive driver behaviour and increased potential for wide network impacts and collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Speed choices | [12 empty] | 0 | 0 |  | 0 | 0
Reductions in speed limits, considering the safety of workers and road users | Road users travel at inappropriate speeds |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Worksite operations | [12 empty] | 0 | 0 |  | 0 | 0
Site in operation during times of night / low visibility | Traffic unable to respond in a timely manner to the hazard ahead |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Works extend outside of approved hours | Interference with traffic flows, business activity and residents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TTM implemention for excessive time within a single shift | Staff fatigue leads to decreased concentration of road workers leading to increased likelihood of incidents |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Incident in / near the work area involving a road accident, breakdown or crash into the worksite | Impacts on works activities, ability to complete works on time, and wider network imacts and delays. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Qualifications for all field staff to meet minium requirements specified | Field staff not complying with detailed requirements for more complex works create hazards for themselves and others. |  |  | Select L & C |  |  |  |  | Select L & C
Complex works activities with multiple different TTM stages / TGS diagrams | TGS and site works not aligned with works not adequately protected |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Radio communiations | Radio communiction disruption / lack of clarity |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Delays to works | Works run over time |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Works occur at innapporiate times of the day |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Extended shift length leads to staff fatugue |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Extended shift time or uncomfortable weather conditions | TTM staff fatigue / heat exhaustion / dehydration |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Constrained site | Limited clearance to traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
| Worker strays into live traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TTM workers required to operate close to worksite vehicles and plant
| Risk to workers during installation / modification / removal of TTM |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Staff complacency due to repetitive work tasks | Workers underestiamte the hazards that they expose themselves to and operate outside of approved safe works procedures |  |  | Select L & C |  |  |  |  | Select L & C
Dedicated roles such as lookout persons | Inappropriate separation of tasks leads to additional tasks being undertaken and lookout role not being undertaken as required. |  |  | Select L & C |  |  |  |  | Select L & C
TC operations mistakenly releasing traffic early before last vehicle in opposing direction has passed | Risk of collision between traffic traveling in opposite directions |  |  | Select L & C |  |  |  |  | Select L & C
Road users not complying with TC instructions | Risk of collision between traffic traveling in opposite directions |  |  | Select L & C |  |  |  |  | Select L & C
PTCD | Failure of PTCD leads to driver confusion and vehicle conflicts |  |  | Select L & C |  |  |  |  | Select L & C
Rough surface alongside worksite where TTM staff are oparating | Slips, trips and falls |  |  | Select L & C |  |  |  |  | Select L & C
Works vehicles undertaking U-turns or turning movements at inappropriate locations | Collisions with other traffic travelling past the site |  |  | Select L & C |  |  |  |  | Select L & C
Workers crossing the road in in apporpriate locations | Risk of injury from collision with traffic travelling past the site |  |  | Select L & C |  |  |  |  | Select L & C
Emergency Vehicles | [12 empty] | 0 | 0 |  | 0 | 0
Works lead to excessive traffic queues and delays leads to unacceptably long delays to road users | Emergency vehicles access past the works area is blocked by works activities or queued traffic leading to unacceptable delays to emergency vehicles |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Emergency vehicle access to the worksite not clear | Extended delay to attend to injured workers or road users at the worksite |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Public Transport | [12 empty] | 0 | 0 |  | 0 | 0
Public transport stops and routes | Passenger and public transport vehicle movements occur in hazardous locations. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Site Access | [12 empty] | 0 | 0 |  | 0 | 0
Site access for construction vehicles is not clearly defined / managed | Construction vehicles stop / queue in unsafe locations causes |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Construction vehicles use inappropriate entry and exit points
| Passing traffic inadvertently enters worksites leading to worker injury |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Congestion at entry leads | Impacts on traffic flow creating wider network impacts and potential for collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Unscheduled deliveries | Impacts on traffic flow creating wider network impacts and potential for collisions |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Exit from work site to high speed roads | Insufficient acceleration length leads to unsafe exit to the traffic stream and collisions with through traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Property Access | [12 empty] | 0 | 0 |  | 0 | 0
Closure or roads or turn movements at intersections affects adjoining properties with access near or at the site | Road users attempting to access properties compromised by road closures or delays |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Parking facilities exist within the proposed worksite | Illegal or unsafe parking practices in and around the worksite. |  |  | Select L & C |  |  |  |  | Select L & C
TTM devices block sight lines for vehicles entering / exiting properties | Potential collisiopns between enetering / exiting traffic and through traffic on the road. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Parking facilities exist within the proposed worksite | Parked vehicles obstruct TTM devices or create hazardous situtations within the worksite. |  |  | Select L & C |  |  |  |  | Select L & C
Site & environmental features | [12 empty] | 0 | 0 |  | 0 | 0
Sight distance to all TTM devices obscured by vegetation, curves, crests or other obstructions | inadequate sight distance able to be achieved leading to hazardous road user situations. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Existing signage, pavement markings and other features conflict with the proposed TTM treatments | Driver confusion |  |  | Select L & C
Electrical storms | Lightning risk to TC and other staff |  |  | Select L & C
Shadowing, fog, glare, inclement weather, smoke | Reduced visibility for approaching traffic - increased risk to road users and road workers |  |  | Select L & C
Night works | Reduced understanding of worksite |  |  | Select L & C
| Visual overload with retroflective devices |  |  | Select L & C
Site constraints with no escape route for workers or traffic controllers | Workers cannot escape traffic incidents on site and are injured by vehicle intrusion into the site. |  |  | Select L & C
Obstructions reducing sight distance for road users along road alignment including barriers, stockpiles, gawk screens, and plant items | increased potential for colliisions with obstructions on the road or other vehicles who have stopped / slowed |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
TC operations near bridges and waterways restrict escape paths | Injury to TC unable to escape from an errant vehicle |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 | High | 0 | 0
Heavy / Oversize vehilcles | [12 empty] | 0 | 0 |  | 0 | 0
Unexpected over-sized loads | Inadequate lane widths leads to vehicles unable to negotiate defined traffic route and collide with other vehicles or worksite devices / plant |  |  | Select L & C
Temporary Traffic Management Devices | [12 empty] | 0 | 0 |  | 0 | 0
Road features makes it difficult for signs to be placed correctly | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
TTM devices dislodged or removed due to wind, passing traffic, theft, vandalism | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Road alignment results in complex requirements for the alignment of TTM devies to ensure their visibility and comprehension by the intended road users | Reduced TTM device effectiveness creating potential confusion or hazardous situations and conflicts. |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Traffic incidents | [12 empty] | 0 | 0 |  | 0 | 0
Vehicles running into the site through delineation | TTM staff hit by traffic |  |  | Select L & C |  |  |  |  | Select L & C |  |  |  | 0 | 0 |  | 0 | 0
Injury to road user
TTM staff operating near works vehicles and plant | TTM staff hit by mobile plant / works vehicles |  |  | Select L & C |  |  |  |  | Select L & C
TC escape bath is blocked / obstructed | Injury to TC if vehicle does not stop at correct location. |  |  | Select L & C |  |  |  |  | Select L & C
Like - lihood
Conse - quence
Rating
Measures selected will generally only reduce the likelihood or consequence of an event, usually not both. Ensure adequate justification is documented here or elsewhere to support the proposed revised ratings.

## Lookups
Risk Matrix
Likelihood Ratings | Consequence ratings |  |  | Almost Certain | Likely | Possible | Unlikely | Rare
Almost Certain | Catastrophic | 1 | Catastrophic | Very High | Very High | High | High | Medium
Likely | Major | 2 | Major | Very High | Very High | High | Medium | Low
Possible | Moderate | 3 | Moderate | High | High | Medium | Low | Low
Unlikely | Minor | 4 | Minor | High | Medium | Low | Low | Low
Rare | Insignificant | 5 | Insignificant | Medium | Low | Low | Low | Negligible